## Slide 1
NIRISS Commissioning
André Martel

## Slide 2
Goals:
Basic checkout or verification of all the modes and mechanisms of NIRISS.
Achieved with a minimum set of pre-planned, coordinated activities to verify/understand the behavior of NIRISS in orbit and to validate/update existing ground calibration data.
Ultimate goal is to enable the start of the scientific use of NIRISS and the scheduling of ERS, EROs, GTO, and GO science observations.
P.S.: CAR = Commissioning Activity Request
Overview

## Slide 3
Nov 2014 – Jun 2015:
Revised and updated all the NIRISS CARs (prime).
Benefit: firmed up the operations (missing OSS scripts  APT, location of subarrays and science pixels, missing mnemonics and FITS header keywords for health/status  FITSWriter, etc…)
Presented the CARs for adjudication to NGAS, STScI, and ISIM at the CTLWG meetings.
Reviewed several JWST OTE CARs that pertain to NIRISS.
Provided monthly status updates of NIRISS to the CTLWG.
Presented the status of the NIRISS CARs at the WFSCOWG meetings.
Cross-SI commissioning team leads meetings at STScI.
Schedule
Note: possible NIRISS in parallel (rules and constraints not yet defined, usefulness, overlaps, mechanism usage)

## Slide 4
Summer/Fall 2015: Timeline updates (Welsh/Biagetti)
Oct 28: Review of the new NIRISS timeline (flow and dependencies) with NGAS and STScI
Nov 10: Adjudication of the ISIM Engineering CARs at the CTLWG
Nov 16: Release of the new official timeline
Schedule

## Slide 5
May 2016 (L-30 months):
Start of proposal submissions with APT: complete on-orbit programs (filters, exposures, dithers, targets)
Undergo internal STScI review (PIT = Proposal Implementation Team) (iterate with schedulers, etc…)
Launch is Oct 1, 2018 and 6-month campaign.
NIRISS/FGS = 80K on Day 42 and 43K on Day 57
NIRCam = 80K on Day 40 and 39K on Day 52
NIRSpec = 80K on Day 37.2 and 39K on Day 52
Schedule

## Slide 6
Three groups of CARs:
ISIM CARs: path to power-on of the SIs (22 but ~9 for NIRISS): IRSU, ICDH, ICE, FPE, etc…
NIRISS CARs: verify/characterize the modes and update reference files (22) (“Engineering” and “Science” CARs)
OTE CARs: telescope alignment/phasing (WFSCOWG)
High-level flow after launch:
ISIM CARs
 NIRISS Engineering CARs (1, 2, 24, 4, 5)
 OTE CARs
 NIRISS Science CARs (7, 8, 9, 10, 12, 13, etc…)
CARs/Timeline

## Slide 7
Targets:
Need targets for several activities: focus, flux standards, wavelength calibrators, NRM binaries, etc…
Some already known, e.g., crowded LMC astrometric field, primary and secondary flux standards.
Need multiple targets in each class for more flexibility in scheduling and availability in the timeline.
When possible, use same targets as other SIs for cross-SI calibration and schedulability, e.g., NIRCAM
When possible, same target for multiple NIRISS CARs, e.g., trending, …
Mechanism usage: PW: 26% FW: 78%
APT readiness for all NIRISS modes (calibration, externals)
NIRISS CARs To-do/Issues